## Slide 1: One system that runs FSA and enforces its policies
PROPOSAL TO FSA INVESTMENT CAPITAL · OCTOBER 2026
Enterprise ERP on Frappe and ERPNext, configured to FSA's policies, with one FSA-specific app that carries every hard stop.
Prepared by Ethereal Purpose Lda. · Response to the Enterprise Business Requirements Document v1.0
Notes: Thank FSA for the invitation. One message: a proven open-source ERP, configured to FSA policies, with one FSA app that enforces the hard stops. We cover the solution, the plan, the team and the full five-year cost.

## Slide 2: Every requirement met, Release 1 live in five months
AT A GLANCE
91 / 91
requirements met
5 Apr 2027
Release 1 live, all Must items
US$133,500
implementation, all three lots
US$0
licence fees, every year
Lot 1 · Must
59 requirements · US$90,400 · live 5 Apr 2027
Lot 2 · Should
27 requirements · US$35,400 · live 26 Jul 2027
Lot 3 · Could
5 requirements · US$7,700 · live 20 Sep 2027
US$350,020 total cost over five years, including hosting, support and a yearly penetration test. FSA can award Lot 1 alone, Lots 1 and 2, or all three.
Notes: The four numbers to remember. Lots map one to one to Must, Should and Could, as FSA asked. Each lot can be awarded on its own.

## Slide 3: We read the EBRD as five commitments
OUR UNDERSTANDING
1
One record per fact
The Deal Data Sheet feeds every memo, register and report; nothing is retyped.
2
Rules as settings
One versioned parameter schedule drives every threshold, timer and approval.
3
Hard stops, not reminders
KYC, screening, limits, signatures and tax tests block the action itself.
4
Evidenced, segregated approvals
Name, role and authority code on every approval; no one creates, checks and approves.
5
Outsourcing inside the system
ITL, CASS, auditors, AAF and funders work in the platform, not by email.
Notes: This is how we read the 31-page EBRD. Every design choice that follows serves one of these five commitments.

## Slide 4: Nine modules on one shared core
SOLUTION
Investment pipeline
Portfolio and loans
Risk and limits
Compliance and KYC
Finance and treasury
Procurement
Travel and missions
Consultants
Governance and Board
FSA Investments app
Approvals engine · parameter schedule · limit table · every hard stop
Frappe Framework (MIT) · ERPNext, Frappe HR, Frappe Lending (GPLv3) · Frappe Insights (AGPLv3)
Connected parties
ITL
MCB
CASS
Microsoft 365
AAF and funders
Hosted on OVHcloud Paris across three availability zones · daily backups at Hetzner, Germany
Notes: Nine EBRD modules all sit on one core. The FSA Investments app holds every rule FSA owns, so thresholds are changed in one place. Outside parties connect to the core, not to individual modules.

## Slide 5: A licensed open-source product, configured as FSA asked
WHY FRAPPE AND ERPNEXT
“Configure, don't build. FSA prefers a proven cloud product, configured with as little custom code as possible.”
EBRD §3, Principle 10 · p.6
“The system is cloud-hosted and bought as a licensed product, not developed from scratch.”
EBRD Appendix G · p.29
US$0
licence fees, for any number of users
Full source code
delivered to FSA under GPLv3, which meets the escrow requirement (App. H)
27 of 91
requirements need code, all in one documented app
Notes: Two sentences from FSA itself justify the choice. Open source also means no licence fees and full code ownership, which covers the escrow requirement in Appendix H.

## Slide 6: 91 requirements: 3 standard, 61 configured, 27 developed
REQUIREMENTS COVERAGE
Chart: 
| Governance and Board | Consultants | Travel and missions | Procurement | Finance and treasury | Compliance and KYC | Risk and limits | Portfolio and loans | Investment pipeline
Standard | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0
Configuration | 6 | 4 | 4 | 4 | 7 | 11 | 5 | 10 | 10
Development | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 6 | 9
Code sits where FSA's rules are specific to an investment vehicle: the IC and Board engine, the limit engine, the Disbursement Pack, the loan register and valuation.
Notes: Most of the 91 requirements are configuration. The 27 developed items are where FSA is unique as an investor: the committee engine, limits, disbursement and the loan register.

## Slide 7: No payment reaches the bank until every check passes
APPROVALS ENGINE AND HARD STOPS
Deal team prepares the Disbursement Pack
Automatic gate
KYC complete
Screening under 30 days old
Within Red limits and caps
IC and Board approvals evidenced
Documents signed under 6 months ago
Cooperative Jurisdiction test passed
MD approves
Panel A + Panel B release
MCB payment
All 24 Appendix F acceptance tests are covered. A failed check returns the Pack to the deal team and is logged; nobody can override it.
Notes: Walk the flow left to right. The MD approve button stays disabled until the gate is fully green. Each check maps to an Appendix F test, AT-01 to AT-24.

## Slide 8: ITL and MCB first: every payment passes through them
INTEGRATIONS
ITL
Works inside the system with its own role; postings by REST API or SFTP
Lot 1
MCB
camt.053 / MT940 in, pain.001 out; host-to-host or secure upload
Lot 1
CASS
CASS users inside the system plus file exchange
Lot 1
Screening
Daily UN list feed; other lists through CASS
Lot 1
Microsoft 365
Entra ID single sign-on, Exchange, SharePoint
Lot 1
Market data
Scheduled import of SOFR, FX rates and DSA
Lot 2
MCB: two ways to connect, same controls
Option 1 · Host-to-host
Statements (camt.053 or MT940) and confirmations arrive automatically, if MCB offers it.
Option 2 · Secure upload, ready on day one
The HFO uploads the daily statement from MCB online banking; the system matches every line.
Formats required: §7.2, p.16 · MCB feeds are FSA's dependency: App. G, p.29
Notes: ITL and MCB are in Lot 1 because every payment depends on them. If MCB has no host-to-host link by go-live, the secure upload gives the same controls from day one.

## Slide 9: Every section 7.3 requirement met in Lot 1
SECURITY AND CONTINUITY
Single sign-on and MFA
Through FSA's Entra ID; step-up MFA on every payment signature
Segregation of duties
Enforced by the approvals engine on every item
Encryption
TLS 1.2/1.3 in transit; AES-256 at rest, including backups
Audit trail
Every change, approval and export logged, append-only
Continuity
Multi-zone live; daily backups at a second provider; RPO 24 h
Independent penetration test
Regional certified firm, before go-live and every year
≥ 99.9% availability a month, monitored 24/7. Verified before go-live by the acceptance tests, a restore test and the penetration test.
Notes: Everything in section 7.3 is in Lot 1, not deferred. The pen test is by an independent regional certified firm, before go-live and yearly.

## Slide 10: Release 1 live 5 April 2027, all lots by September
DELIVERY PLAN
Nov 2026
Dec
Jan 2027
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Lot 1
US$90,400
Live 5 April 2027
Lot 2
US$35,400
Live 26 July 2027
Lot 3
US$7,700
Live 20 September 2027
Design
Build sprints
System test
UAT and training
Go-live and hypercare
Same five phases for each lot. Two-week sprints end with a demo to FSA; Ethereal Purpose runs system tests, FSA runs UAT.
Notes: Design week starts 16 November 2026. Lot 1 has 14 weeks of build, then system test, UAT and go-live on 5 April 2027. Lots 2 and 3 follow back to back.

## Slide 11: Nine roles, one named lead, 800 person-days
TEAM
Role | Day rate | Lot 1 | Lot 2 | Lot 3
Engagement lead | $280 | 24.7 | 11.5 | 1.5
Functional consultant | $230 | 71.2 | 32.5 | 8
Lead developer | $180 | 88 | 49.5 | 5
Senior developer, finance | $180 | 77 | – | –
Developer, governance | $135 | 80.5 | 47 | 27
Developer, operations | $135 | 69 | 42 | –
Developer, reports | $135 | 69 | – | –
QA engineer | $120 | 46.4 | 25 | 7
DevOps engineer | $180 | 12.8 | 4.5 | 0.5
Total person-days |  | 539 | 212 | 49
A Tunisia-based Frappe team working Mauritius office hours; the engagement lead and functional consultant are on site for kick-off and the Lot 1 go-live.
Notes: Price is built bottom-up from this table: each person’s days on each phase times their day rate. Every role has a named back-up.

## Slide 12: Fixed price per lot, paid on accepted milestones
FINANCIAL OFFER
LOT 1 · MUST
US$90,400
59 requirements · live 5 April 2027
LOT 2 · SHOULD
US$35,400
27 requirements · live 26 July 2027
LOT 3 · COULD
US$7,700
5 requirements · live 20 September 2027
20%
Signature
30%
Design signed off
30%
UAT and Appendix F tests passed
20%
Live + 30 days stable
Recurring: support US$3,000 a month from Lot 1 go-live · hosting US$375 a month · penetration test US$4,500 before go-live, then US$3,000 a year · licences US$0.
Notes: Fixed price per lot, paid on four accepted milestones: 20, 30, 30, 20. FSA only pays the large tranches once it has signed off design and passed UAT.

## Slide 13: US$375 a month, built from OVHcloud's public price list
HOSTING
Chart: 
| Contingency | Backups, second provider | Backups, first copy | Monitoring and secrets | Test and UAT | Live
US$ per month | 24.1 | 4.06 | 9.59 | 20.14 | 80.52 | 236.58
Fixed monthly fee, year 1
US$375
Two of everything in live
in different Paris zones, for ≥ 99.9% availability
Full hourly list price
no Savings Plan discount assumed
No traffic charges
between zones or to the internet
Backups at a second provider
Hetzner, Germany, as §7.3 requires
US$23,891 over five years
+3% a year from year 2
Notes: Every line is an OVHcloud or Hetzner public list price, read on 18 October 2026: about US$351 a month, plus US$24 contingency for exchange rate and price changes. The detail is on the proposal page and in the Excel annex.

## Slide 14: US$350,020 over five years, with no licence fees
TOTAL COST OF OWNERSHIP
Chart: 
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Implementation | 133500 | 0 | 0 | 0 | 0
Hosting | 4500 | 4635 | 4774 | 4917 | 5065
Support | 21000 | 37080 | 38192 | 39338 | 40518
Penetration test | 4500 | 3000 | 3000 | 3000 | 3000
Implementation, 3 lots
US$133,500
Support and maintenance
US$176,129
Hosting and backups
US$23,891
Penetration tests
US$16,500
Software licences
US$0
Five-year total
US$350,020
Notes: Year 1 carries the three lots. From year 2 FSA pays only support, hosting and the yearly penetration test, about US$45,000 a year, rising 3% a year.

## Slide 15: Four decisions to start on 16 November
NEXT STEPS
1
Choose the lots
Lot 1 alone, Lots 1 and 2, or all three
2
Confirm hosting location
EU hosting (France, backups in Germany), or the African-region option
3
Sign and kick off
Contract by 13 November 2026, design week from 16 November
4
Open the MCB conversation
Ask MCB about host-to-host; secure upload works from day one
Ethereal Purpose Lda. · Thank you
Notes: Close on the four decisions. Confirm the next contact date for questions before the award.